## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 24/10/2022-30/10/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code: Login with Facebook | AnNT | In Progress | Styling in progress
2 | Code: Login with Google | AnNT | Pending | Waiting for registration with Google
3 | Study Angular | GiangNT | Completed
4 | Study OData | GiangNT, HuyenBN | Completed
5 | Design Front-end for Pages | KienNT, HuyenBN | Completed | All Screens
6 | Landlord Upload House Information | AnNT | In Progress | API, Angular, Front-end Design
7 | Database Population | KienNT | Completed
8 | (Landlord) Manage Rooms | ThongPQ | In Progress | API + Angular
9 | (Staff) Dashboard | HuyenBN | In Progress | API + Angular + Design Front-end
10 | Home Page: Search & Filter with OData | GiangNT | In Progress | API + Angular
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Study Angular | HuyenBN | In Progress | Not finished
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study OCE LOT | AnNT, GiangNT | 2022-06-11
2 | Continue Coding main functionalities | All Team | 2022-06-11
3 | Continue Updating documentations | All Team | 2022-06-11
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue