## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 31/10/2022-06/11/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code: Login with Facebook | AnNT | In Progress | Finished with testing accounts
2 | Code: Login with Google | AnNT | Completed
3 | (Guest) House Detail, Room Detail | KienNT | Completed | Design Front-end + Angular + API
4 | Database Design & Population | KienNT, HuyenBN | Completed
5 | Design Front-end for Pages | KienNT | Completed | All Screens
6 | Landlord Upload House Information | AnNT | In Progress | API, Angular, Front-end Design
7 | Home Page: Search & Filter with OData | GiangNT | In Progress | API + Angular
8 | (Landlord) Manage Rooms | ThongPQ | In Progress | API + Angular
9 | (Staff) Dashboard | HuyenBN | In Progress | API + Angular + Design Front-end
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study OCE LOT | AnNT, GiangNT | 2022-06-11
2 | Home Page | GiangNT | 2022-06-11 | Finish coding, Update style
3 | (Landlord) Upload House Information | AnNT | 2022-06-11 | 2 methods
4 | (Landlord) Manage Rooms | ThongPQ | 2022-06-11 | Fix bugs
5 | (Staff) Dashboard | HuyenBN | 2022-06-11 | Finish
6 | Documentation: Report 4 | All Team | 2022-06-11 | Submission
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Test Web Responsive directly on Mobile Phone | GiangNT | 2022-09-11 | By running localhost on internal wifi
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue