## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 14/11/2022-20/11/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Documentation: Report 4 | All Team | Completed
2 | (Landlord) Manage Houses | ThongPQ, KienNT | In Progress | API, Angular
3 | Landlord Upload House Information | AnNT | In Progress | API, Angular, Front-end Design
4 | (Landlord) Manage Rooms | ThongPQ | Completed | Fix Bug
5 | (Staff) List Report | HuyenBN | In Progress | API, Angular, Front-end Design
6 | Home Page | GiangNT | In Progress | Responsive
7 | (Guest) House Detail | KienNT | Completed | Update List Room
8 | Documentation: Report 2 | AnNT | Completed | Update
9 | (Staff) List House, List Order, Dashboard | HuyenBN, KienNT | Completed | Update
10 | Database Design | HuyenBN, GiangNT | Completed | Update
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Set up Server for storing Images | AnNT | 27/11/2022
2 | Set up Server for deployment | AnNT | 27/11/2022
3 | Document: Report 1 | HuyenBN | 27/11/2022 | Update
4 | Document: Report 2 | AnNT | 27/11/2022 | Update
5 | Login / Register | AnNT | 27/11/2022 | Update
6 | Document: Report 4 | ThongPQ, HuyenBN | 27/11/2022 | Update
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Store images on Server: Amazon S3 | GiangNT | 17/11/2022
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue