## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 10/10/2022-16/10/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code: Login with Facebook | AnNT | In Progress | Register system with Facebook in progress
2 | Code: Login with Google | AnNT | In Progress | Register system with Google in progress
3 | Report 4 - Software Design Document | KienNT, GiangNT | In Progress | Package Diagram
4 | [API] Home Page | ThongPQ | Completed | Get List House & Search by Name
5 | [Database] Data Population | HuyenBN, KienNT | Completed
6 | [Angular] Home Page | KienNT, GiangNT | Completed | Get List House & Search by Name
7 | [Front-end] House Detail | HuyenBN | Completed
8 | [API + Angular] House Detail | ThongPQ, GiangNT, HuyenBN | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Study Angular | GiangNT, HuyenBN | In Progress | Not finished
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study Angular | GiangNT, HuyenBN | 23/10/2022
2 | Study OCE LOT | AnNT, GiangNT | 23/10/2022
3 | Code: Login with Facebook | AnNT | 23/10/2022 | Finish
4 | Code: Login with Google | AnNT | 23/10/2022 | Finish
5 | Continue Coding main functionalities | All Team | 23/10/2022
6 | Continue Updating documentations | All Team | 23/10/2022
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue