## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 05/12/2022-11/12/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | (Landlord) Manage Houses | ThongPQ, KienNT | Completed | API, Angular
2 | Landlord Upload House Information | AnNT | Completed | API, Angular, Front-end Design
3 | (Staff) List Report | HuyenBN | In Progress | API, Angular, Front-end Design
4 | Test API Using NUnit | All Team | In Progress
5 | Integration Test | All Team | In Progress
6 | Set up Server for deployment | AnNT, GiangNT | Completed | Amazon S3, Vercel
7 | Login, Landlord Register | HuyenBN, GiangNT | Completed | Front-end Design, Responsive
8 | (Login) Logout | AnNT | Completed
9 | (Staff) Update Profile | KienNT | Completed
10 | (Document) System Architecture | ThongPQ | In Progress
11 | (Responsive) Staff's Screens | KienNT | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Landlord Add Rooms | AnNT | 18/12/2022
2 | Test API Using NUnit | All Team | 18/12/2022
3 | Integration Test | All Team | 18/12/2022
4 | Finish all Documents | All Team | 18/12/2022
5 | (Admin) Manage Accounts | AnNT, ThongPQ | 18/12/2022
6 | (Staff) Change Password | AnNT | 18/12/2022
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Front-end Server Deployment on Vercel | GIangNT | 2022-08-12
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue