## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 07/11/2022-13/11/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Documentation: Report 4 | All Team | In Progress
2 | (Staff) Dashboard | HuyenBN | Completed | API, Angular, Front-end Design
3 | Documentation: Report 1 | HuyenBN | Completed | Fix & Update
4 | (Landlord) Manage Houses | ThongPQ, KienNT | In Progress | API, Angular
5 | Home Page: Search & Filter with OData | GiangNT | Completed
6 | Landlord Upload House Information | AnNT | In Progress | API, Angular, Front-end Design
7 | (Landlord) Manage Rooms | ThongPQ | In Progress | Fix Bug
8 | Set up Google Map API | GiangNT | Completed | Create billing account
9 | Database: Update | GiangNT, HuyenBN | Completed
10 | (Staff) List Report | HuyenBN | In Progress | API, Angular, Front-end Design
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study OCE LOT | AnNT, GiangNT | 20/11/2022
2 | Home Page | GiangNT | 20/11/2022 | Finish coding, Update style
3 | (Landlord) Upload House Information | AnNT | 20/11/2022 | 2 methods
4 | (Landlord) Manage Rooms | ThongPQ | 20/11/2022 | Fix bugs
5 | (Staff) List Order | HuyenBN | 20/11/2022 | Finish
6 | (Landlord) Register | AnNT | 20/11/2022 | Complete
| (Admin) Create Account | AnNT |  | API, Angular
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue