## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 05/09/2022-11/09/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Collect Requirement | All Team | In Progress
2 | Set up Code Environment | All Team | In Progress | .NET 5, Angular 12, SQL Server 2019
3 | Set up Collaboration Tools | GiangNT | Completed | Facebook, Messenger, Discord, Github, MS Office, Jira, Figma
4 | Learn Anguar | ThongPQ, KienNT | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
chốt đề tài
1 | Weekly Report | GiangNT | Pending | Not finished
Pending
Pending
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Use Case Diagram | HuyenBN | 18/09/2022
2 | Learn Angular | ThongPQ, KienNT, AnNT | 18/09/2022
3 | Meet with Client | All Team | 18/09/2022
4 | Screen Wireframe | All Team | 18/09/2022
5 | Screen Mockup | All Team | 18/09/2022
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Draw Use Case Diagram before Wireframe | GiangNT | 2022-11-09
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D12: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue