## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 28/12/2022-04/12/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | (Landlord) Manage Houses | ThongPQ, KienNT | In Progress | API, Angular
2 | Landlord Upload House Information | AnNT | In Progress | API, Angular, Front-end Design
3 | Home Page | GiangNT | Completed
4 | (Staff) List Report | HuyenBN | In Progress | API, Angular, Front-end Design
5 | Test API Using NUnit | All Team | In Progress
6 | Integration Test | All Team | In Progress
7 | Header of Pages | GiangNT, KienNT | Completed | Angular
8 | (Guest) House Detail | KienNT | Completed | Rate & Comment
9 | (Guest) Create Order, Send Report | KienNT, ThongPQ | Completed | API, Angular, Front-end Design
10 | (Staff) List Landlord Sign up Request | HuyenBN | Completed | API, Angular, Front-end Design
11 | (Admin) Manage Staffs | KienNT | In Progress | API, Angular, Front-end Design
12 | Set up Server for deployment | AnNT | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Document: Report 1 | HuyenBN | 2022-11-12 | Update
2 | Document: Report 2 | AnNT | 2022-11-12 | Update
3 | Document: Report 4 | ThongPQ, HuyenBN | 2022-11-12 | Update
4 | Landlord Upload House Information | AnNT | 2022-11-12 | Finish
5 | Test API Using NUnit | All Team | 2022-11-12 | Finish
6 | Integration Test | All Team | 2022-11-12 | Finish
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Server Deployment on Amazon S3 | AnNT | 24/11/2022
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue