## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 12/09/2022-18/09/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Draw Wireframes | All Team | In Progress | Using Figma
2 | Make Prototypes | All Team | In Progress | Using Figma
3 | Design Database | All Team | Completed | Using SQL Server
4 | Meet with Client | All Team | Completed | Finish Requirement
5 | Collect Administrative Unit Data | GiangNT | Completed | Excel File
6 | Draw Use Case Diagram | HuyenBN | In Progress
7 | Code: Test Connection between Projects | GiangNT | Completed | API connect to Database, Web Client connect to API
8 | Demo Function: Import file Excel | AnNT | In Progress | Code Demo
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Use Case Diagram | HuyenBN | In Progress | Not finished
2 | Screen Mockup | All Team | Pending | Not started
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Use Case Diagram | HuyenBN | 25/09/2022
2 | Screen Mockup | All Team | 25/09/2022
3 | Design Document | KienNT | 25/09/2022 | Database Tables Description
4 | Database Design | All Team | 25/09/2022 | Confirm with Mentor
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D16: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue