## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 12/12/2022-18/12/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | (Document) System Architecture | ThongPQ | Completed
2 | (Responsive) Staff's Screens | KienNT | Completed
3 | (Staff) List Report | HuyenBN | Completed | API, Angular, Front-end Design
4 | Test API Using NUnit | All Team | Completed
5 | Integration Test | All Team | Completed
6 | All Documentation | All Team | Completed
7 | Finish Coding | All Team | In Progress | Fixing final bugs
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Practice Presentation | All Team | 25/12/2022
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue