## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 17/10/2022-23/10/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code: Login with Facebook | AnNT | In Progress | Register system with Facebook in progress
2 | Code: Login with Google | AnNT | In Progress | Register system with Google in progress
3 | [Database] Data Population | KienNT | Completed
4 | [Documentation] Report 4: SDD | ThongPQ | Completed | System Architecture: Component Description
5 | Landlord Dashboard | ThongPQ | Completed | API
6 | Landlord List Rooms | HuyenBN | Completed | Front-end Design
7 | Landlord Dashboard | KienNT | In Progress | Front-end Design, Angular
8 | Student Report | ThongPQ | In Progress | API, Angular, Front-end Design
9 | Home Page | HuyenBN | In Progress | Front-end Design: Fix Responsive
10 | Landlord Upload House Information | AnNT | In Progress | API, Angular, Front-end Design
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Study Angular | GiangNT, HuyenBN | In Progress | Not finished
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study Angular | GiangNT, HuyenBN | 30/10/2022
2 | Study OCE LOT | AnNT, GiangNT | 30/10/2022
3 | Code: Login with Facebook | AnNT | 30/10/2022 | Finish
4 | Code: Login with Google | AnNT | 30/10/2022 | Finish
5 | Continue Coding main functionalities | All Team | 30/10/2022
6 | Continue Updating documentations | All Team | 30/10/2022
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue