## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 19/09/2022-25/09/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Draw Wireframes | All Team | In Progress | Using Figma
2 | Draw Screen Mock-ups | All Team | In Progress | Using Figma
3 | Use Case Diagram | HuyenBN | Completed
4 | Design Document | KienNT, GiangNT | In Progress | Database Tables
5 | Database Design | All Team | In Progress | Confirm with Mentor
6 | Demo Function: Import file Excel | AnNT | Completed | Code Demo
7 | Code: Test Connection between Projects | All Team | Completed | API connect to Database, Web Client connect to API
8 | Study Angular | ThongPQ, KienNT | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Use Case Diagram | HuyenBN | In Progress | Not finished
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Screen Flow Diagram | GiangNT | 2022-02-10
2 | Screen Mock-ups | All Team | 2022-02-10
3 | Draw Wireframes | All Team | 2022-02-10
4 | Study Angular | GiangNT, HuyenBN, AnNT | 2022-02-10
5 | Entity Relationship Diagram | HuyenBN | 2022-02-10
6 | Study OCE LOT | AnNT, GiangNT | 2022-02-10
7 | Code: Login with Facebook | AnNT | 2022-02-10
8 | Code: Login with Google | AnNT | 2022-02-10
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D16: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue