## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 03/10/2022-09/10/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code: Login with Facebook | AnNT | In Progress | API Done
2 | Code: Login with Google | AnNT | In Progress | API Done
3 | Draw Screen Mock-ups | All Team | In Progress | Using Figma
4 | Entity Relationship Diagram | HuyenBN | Completed
5 | Design Document | ThongPQ, GiangNT | In Progress | System Architecture Diagram, Database Tables
6 | Database Design | GiangNT | Completed | Update
7 | Report 1 - Project Introduction | All Team | Completed
8 | Report 2 - Project Management Plan | All Team | Completed
9 | Report 3 - Software Requirement Specification | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Study Angular | GiangNT, HuyenBN | In Progress | Not finished
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study Angular | GiangNT, HuyenBN | 16/10/2022
2 | Study OCE LOT | AnNT, GiangNT | 16/10/2022
3 | Code: Login with Facebook | AnNT | 16/10/2022 | Angular Done
4 | Code: Login with Google | AnNT | 16/10/2022 | Angular Done
5 | Start Coding main functionalities | All Team | 16/10/2022
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue