## Wx
PROJECT REPORT
Group | SEP490_G1
Week | 26/09/2022-02/10/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code: Login with Facebook | AnNT | In Progress | API Done
2 | Code: Login with Google | AnNT | In Progress | API Done
3 | Draw Screen Flow Diagrams | GiangNT | Completed | Using Draw.io
4 | Draw Screen Mock-ups | All Team | In Progress | Using Figma
5 | Entity Relationship Diagram | HuyenBN | In Progress
6 | Design Document | GiangNT | In Progress | Database Tables
7 | Database Design | GiangNT | In Progress | Update
8 | Study Angular | AnNT | Completed
9 | Database Population | KienNT, GiangNT | In Progress
10 | Front-End Design: Home Page | ThongPQ, KienNT | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Study Angular | GiangNT, HuyenBN | In Progress | Not finished
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Study Angular | GiangNT, HuyenBN | 2022-09-10
2 | Study OCE LOT | AnNT, GiangNT | 2022-09-10
3 | Code: Login with Facebook | AnNT | 2022-09-10 | Angular Done
4 | Code: Login with Google | AnNT | 2022-09-10 | Angular Done
5 | Database Design | GiangNT | 2022-09-10 | Finish updating
6 | Entity Relationship Diagram | HuyenBN | 2022-09-10 | Change following changes in Database Design
7 | Write Report 1, 2, 3 | All Team | 2022-09-10 | Documentation
8 | Start Coding main functionalities | All Team | 2022-09-10
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue